VERITAS CONCEPT ENGINEERING

Facilities Planning Consulting — Robin Owens

FRF · PHASE 3 OF 4 · PROVE THE NUMBERS

Prove the Numbers

Facility Readiness Framework — Phase 3 of 4

The scope Phase 2 defined gets priced, scheduled, risk-assessed, and scored — the point where a technically sound layout either holds up under financial and schedule scrutiny or doesn't. Steps 1-5 build the four Facility Readiness Score categories that don't exist yet; Step 6 scores all eight categories together, immediately before Gate 3; Step 7 is the formal decision.

| GATE 3 Numbers Proven | ACCOUNTABLE The CFO or finance lead and the facilities director, jointly |
| --- | --- |
| GATE QUESTION Is every number in this package — cost, schedule, risk — traceable to a real basis, and does the Facility Readiness Score reflect that honestly? | WHAT ACTUALLY GETS SKIPPED An unvalidated budget or an imposed schedule carried into a board presentation as if it were real — the same capital a project is about to ask for, gambled against numbers nobody actually built. |

Running the Gate

Steps in order, facilitated by you or the owner's project lead. Each form named below is its own standalone document in this phase's Forms folder.

1.  Confirm — lock the scope basis

Pull forward the Gate 2 Decision Record, the selected Block Layout Alternative, and the Capacity Model Worksheet. This is the scope, not a topic for renegotiation — a real change belongs in a reopened Gate 2 decision.

→ Form: Scope Basis Confirmation

2.  Estimate — price the confirmed scope for real

Get a scope-based cost estimate tied to the Activity List, Space & Density, and Capacity Model worksheets — not a per-square-foot rule of thumb. Size contingency to how firm the scope actually is.

→ Form: Cost Estimate Summary

3.  Schedule — build real durations, not an imposed date

Build a schedule from actual activity durations. Identify long-lead items specifically — the most common reason a schedule that looked fine on paper slips in execution.

→ Form: Schedule Summary & Long-Lead Items Worksheet

4.  Assess — build the risk list and approval map, honestly

List real risks with a named owner each. Map every approval and permit against a realistic timeline. Write down the key assumptions the whole package rests on.

→ Form: Risk Register & Key Assumptions, Approval & Timeline Map

5.  Strategize — choose a delivery and procurement approach on purpose

Pick a delivery method deliberately, based on this project's actual risk profile and schedule pressure — not by default. Be honest about in-house capacity to manage it.

→ Form: Delivery & Procurement Strategy Worksheet

6.  Score — run the Facility Readiness Score across all eight categories

Score the project in the Facility Readiness Score workbook — the same instrument that's been in the background since Phase 1, now run for the record against real numbers.

→ Form: Facility Readiness Score — Scoring Summary

7.  Decide — close Gate 3 with the CFO and facilities director together

Bring the score, the cost estimate, the schedule, and the top risks to a real decision meeting. 80-100 is Candidate for Gate 3 Review; 60-79 is Additional Definition Required — close the gaps before Gate 3, or get the CFO and facilities director to accept each one explicitly as a named risk; below 60 is Not Ready for Gate 3. Gate 2 Not Satisfied overrides any of these.

→ Form: Gate 3 Decision Record

The Forms for This Phase

Scope Basis Confirmation — Locks down exactly what's being priced, scheduled, and scored.

Cost Estimate Summary — A scope-based estimate by category, not a round number.

Schedule Summary & Long-Lead Items Worksheet — Real durations and the items most likely to determine the finish date.

Risk Register & Key Assumptions — Every real risk with a named owner; the assumptions the estimate depends on.

Approval & Timeline Map — Every approval or permit needed, against a realistic timeline.

Delivery & Procurement Strategy Worksheet — A deliberate delivery method and procurement approach.

Facility Readiness Score — Scoring Summary — All eight categories, traced back to the form that produced each score.

Gate 3 Decision Record — The artifact that closes Phase 3 and starts Phase 4.

A technically sound project with numbers finance doesn't trust won't get funded, and a financially tidy number with no real technical basis won't survive execution. Neither role owns this gate alone.