VERITAS CONCEPT ENGINEERING

Facilities Planning Consulting — Robin Owens

# FRF Phase 3 — Worked Example

Illustrative sample data for all eight Phase 3 templates

This shows Phase 3 filled in, not blank. It picks up the same fictional company used in the Phase 1 and Phase 2, Step 1 Worked Examples — an electronics contract manufacturer expanding an SMT assembly and test line — right where the Phase 2 Gate 2 Decision Record leaves off: layout selected, capacity and resource/equipment counts set, space and relationships defined. Sample answers are shown in navy to distinguish them from the actual blank Facilitator Guide.

Notice the numbers stay honest across all three worked examples rather than getting cleaner as the project moves forward. Phase 1's Rough-Order Budget Range Worksheet gave a wide $650,000-$1,100,000 range; Phase 3's Cost Estimate Summary lands at $965,000 — inside that range, but a real number built from firm vendor quotes and a GC budgetary proposal, not a guess that happened to land in the middle. The FRS Scoring Summary totals 87 out of 100 — Candidate for Gate 3 Review, but not a clean sweep: Site & Physical/Regulatory Constraints and Schedule Realism & Sequencing both lose a couple of points to genuinely open items (a utility-company outage still being scheduled, a permit not yet submitted), and the Gate 3 Decision Record's rationale says so plainly instead of rounding up. That is the discipline this guide is built to produce — a score and a decision that survive a real board or lender asking hard questions.

1. Scope Basis Confirmation — filled example

Pulled directly from the (fictional) Gate 2 Decision Record — nothing here is re-derived or re-guessed.

| Project / Initiative Name | SMT Assembly & Test Line Expansion — Building 2 |
| --- | --- |
| Gate 2 Approval Date | August 18, 2026 |
| Selected Block Layout Alternative (name / reference) | Alternative B — SMT Line 3 sited at the north end of Building 2, in line with Kitting and Reflow/AOI; Functional Test Lab expansion sited adjacent to Hand Assembly, physically separated from the SMT floor for ESD/vibration isolation (per the Weighted-Factor Scorecard and the Relationship Chart's X-rated SMT/Test pairing). |
| Total GSF (from Space & Density Worksheet) | 18,500 GSF (interior building addition + reconfiguration; excludes site-only items — parking, truck court, stormwater infrastructure — carried separately) |
| Total Net New Machines / Equipment (from Capacity & Capacity Model Worksheet) | 8 net new: 1 pick-and-place system, 1 stencil printer, 1 reflow oven (SMT Line 3); 1 AOI system upgrade; 4 functional test stations |
| Executive Directives Still Open (cross-check the Directives Log's Status column) | One: "No utilities on the production floor — all overhead" was marked "pending confirmation against selected layout" at Gate 2. Confirmed here as satisfied — Alternative B routes 100% of new utility drops overhead per the Utility Requirements Summary. All other four directives closed at Gate 2. |
| Any Scope Changes Since Gate 2 — should be none; describe here if anything has changed | None. Scope, layout, and resource/equipment counts match the Gate 2 Decision Record exactly. |
| Prepared By / Date | R. Owens, Veritas Concept Engineering / September 2026 |

2. Cost Estimate Summary — filled example

Nine categories, each with a stated basis — vendor quotes for the equipment line (the largest and most schedule-critical item), GC budgetary numbers for construction, a percentage-of-construction allowance for design fees. Contingency is sized down from Phase 1's wide range because the scope is now locked and the biggest cost driver is a firm quote, not a guess.

| Cost Category | Basis / Source | Amount ($) | % of Total | Notes |
| --- | --- | --- | --- | --- |
| Site Work & Civil | Civil engineer's site plan — Truck Court expansion, stormwater detention pond upsize | $70,000 | 7.3% | Bid-ready |
| Building Shell / Renovation | GC budgetary proposal — shell tie-in for SMT Line 3 bay, solar-ready roof reinforcement (Directives Log) | $140,000 | 14.5% | Bid-ready |
| Interior Fit-Out | GC budgetary proposal — ESD flooring/grounding; no permanent walls between SMT and hand-assembly, per Directives Log | $95,000 | 9.8% | Bid-ready |
| Process Equipment & Machinery (Net New) | Firm vendor quotes — pick-and-place, stencil printer, reflow oven, AOI upgrade, 4 test stations (Capacity & Capacity Model Worksheet) | $410,000 | 42.5% | Quotes valid 90 days |
| Utilities & MEP | MEP engineer's estimate — 208V/3-phase service, 100% overhead utility distribution, compressed air, humidity control | $95,000 | 9.8% | Utility coordination underway |
| Furniture, Fixtures & Equipment (FF&E) | Vendor quotes — adjustable-height assembly stations, ESD workstation furniture | $35,000 | 3.6% |  |
| Design & Engineering Fees | 8% of construction cost — architect, MEP, civil, structural | $45,000 | 4.7% |  |
| Permits & Fees | Municipal building permit + fire marshal review, per jurisdiction fee schedule | $15,000 | 1.6% |  |
| Contingency | 6.2% — sized lower than Phase 1's rough range because Gate 2 layout is locked and the largest line item (equipment) is a firm quote | $60,000 | 6.2% |  |
| TOTAL |  | $965,000 | 100% |  |

3. Schedule Summary & Long-Lead Items Worksheet — filled example

Milestones run roughly 10 months, Design Development through Occupancy/Ramp-Up. Long-lead procurement starts in parallel with Design Development, not after it — the pick-and-place system's 22-week lead time is what actually paces this schedule, which is why it's called out separately below rather than buried inside a single "Procurement" milestone.

| Milestone / Phase | Duration | Target Start | Target Finish | Dependencies / Notes |
| --- | --- | --- | --- | --- |
| Design Development | 8 weeks | Oct 2026 | Dec 2026 | Vendor equipment drawings needed for MEP/structural coordination |
| Permitting | 6 weeks | Dec 2026 | Jan 2027 | Runs concurrent with late Design Development |
| Long-Lead Procurement | 20 weeks | Oct 2026 | Feb 2027 | Pick-and-place system is the long-lead driver — order at Design Development kickoff |
| Bid / Award (if applicable) | 3 weeks | Jan 2027 | Feb 2027 | GC bid for civil/shell/fit-out package only; equipment already sole-sourced |
| Construction / Installation | 14 weeks | Feb 2027 | May 2027 | Cannot start structural tie-in until permit is issued |
| Commissioning | 4 weeks | May 2027 | Jun 2027 | Equipment install complete, utilities live |
| Occupancy / Ramp-Up | 8 weeks | Jun 2027 | Aug 2027 | Phased ramp to the Year 1 throughput target |

Long-Lead Items — the five items whose order-by date, not their installation date, is what actually protects the finish date.

| Item | Lead Time (weeks) | Order-By Date | Status |
| --- | --- | --- | --- |
| Pick-and-Place System (SMT Line 3) | 22 weeks | Oct 2026 | Vendor quote in hand — order upon Gate 3 approval |
| Reflow Oven (SMT Line 3) | 18 weeks | Oct 2026 | Vendor quote in hand |
| AOI System Upgrade | 16 weeks | Nov 2026 | Firm quote received |
| Switchgear / 208V Service Upgrade | 20 weeks | Oct 2026 | Utility coordination in progress |
| Stencil Printer | 10 weeks | Dec 2026 | Standard lead time, not schedule-critical |

4. Risk Register & Key Assumptions — filled example

Six risks, each with a named owner — three of the six are the CFO/facilities-director's or Operations' to manage directly, not Robin's. Likelihood and Impact are rated separately so the two schedule-critical, high-impact risks (equipment lead time, production disruption during tie-in) don't get lost next to the lower-impact ones.

| Risk | Category | Likelihood | Impact | Owner | Mitigation / Response | Status |
| --- | --- | --- | --- | --- | --- | --- |
| Pick-and-place delivery slips past the 22-week quoted lead time | Schedule | Medium | High | R. Owens / Procurement | Order immediately on Gate 3 approval; track vendor milestones monthly; identify a backup vendor as fallback | Open |
| 208V/3-phase service upgrade needs a utility-scheduled outage | Schedule | Medium | Medium | Facilities Director | Engage the utility company at Design Development kickoff, not at construction start | Open |
| Municipal permit review takes longer than the 6-week estimate | Schedule / Regulatory | Medium | Medium | Facilities Director | Pre-submittal meeting before formal submission; permit expediter on retainer | Open |
| SMT equipment vendor pricing increases before PO is issued | Cost | Low | Medium | CFO / Finance Lead | Vendor quote holds 90 days from Gate 3 approval; issue PO within that window | Open |
| Production disruption to existing SMT Lines 1-2 during tie-in | Technical / Operational | Medium | High | VP Operations | Sequence shell/utility tie-in to 3rd-shift/weekend windows; coordinate with Operations | Open |
| Functional test technician hiring doesn't keep pace with ramp | Market / Labor | Medium | Medium | VP Operations | Begin recruiting at Construction start, not Occupancy; use Calibration Lab techs as a bridge | Open |

| Assumption | If This Changes… | Response / Trigger |
| --- | --- | --- |
| Construction material pricing holds within 5% of the Q3 2026 estimate basis | Pricing moves more than 5% | Re-run the Cost Estimate Summary; flag the delta to the CFO before releasing the GC bid package |
| Municipal permit review runs the typical 6 weeks for this jurisdiction | Actual review exceeds 8 weeks | Compress Construction/Installation float; notify the CFO/facilities director the Gate 3 schedule needs revisiting |
| The pick-and-place vendor's quoted 22-week lead time holds | Lead time extends past 26 weeks | Activate the backup vendor identified on the Risk Register, even at a cost premium |
| The Year 1 throughput target (55,000 boards/month) remains the funding basis | Sales revises the Year 1 target materially, up or down | Recheck the Capacity & Capacity Model Worksheet and the Cost Estimate Summary before proceeding to Phase 4 |

5. Approval & Timeline Map — filled example

Five approvals, each mapped to a realistic timeline from the actual issuing authority — notice the utility service upgrade (16-20 weeks) is the longest of the five and shows up on the Risk Register above for exactly that reason.

| Approval / Permit Needed | Issuing Authority | Typical Timeline | Status | Owner |
| --- | --- | --- | --- | --- |
| Building Permit — shell modification & fit-out | City Building Department | 6-8 weeks | Pre-submittal scheduled | Facilities Director |
| Fire Marshal Review — fire lane, life safety, fume extraction | County Fire Marshal's Office | 3-4 weeks, concurrent | Not yet submitted | Facilities Director |
| Utility Service Upgrade Approval — 208V/3-phase | Regional Utility Co. | 16-20 weeks incl. equipment | Initial application submitted | Facilities Director |
| Stormwater / Detention Pond Modification Permit | County Stormwater Mgmt. | 8-10 weeks | Civil engineer preparing application | Facilities Director |
| Air Permit Amendment — conformal coating booth (if triggered) | State Environmental Agency | 10-12 weeks if required | Applicability review in progress | Quality / EHS Lead |

6. Delivery & Procurement Strategy Worksheet — filled example

A deliberate, stated choice — Design-Bid-Build for the construction package, sole-source for the equipment — with the reasoning written out, not just the method named.

| Delivery Method Selected — Design-Bid-Build / Design-Build / CM at Risk / Integrated Project Delivery / Other | Design-Bid-Build for the civil/shell/interior fit-out package; equipment is sole-sourced/negotiated directly with the existing SMT equipment vendor |
| --- | --- |
| Rationale for This Method | The layout and space plan are already fully defined from Phase 2, so Design-Build's early contractor input has little value here — a competitive GC bid on a well-defined scope controls cost better. The SMT equipment is sole-sourced because Lines 1 and 2 already run this vendor's platform; matching it avoids a second training/spares/service relationship. |
| Owner's In-House Capacity to Manage This Delivery Method | The facilities director has run two smaller renovation projects with this same delivery method; no outside owner's-rep is needed. Equipment install is vendor-managed per their standard installation contract. |
| Procurement Approach — Competitive Bid / Negotiated / Sole-Source / Other | Competitive Bid for the GC package (minimum 3 bids); Sole-Source/Negotiated for the SMT equipment and AOI upgrade |
| How This Matches the Project's Risk Tolerance | Scope is well-defined and low-novelty — an addition to an existing, proven line type — which fits a low-risk-tolerance, cost-certainty preference from the CFO via competitive bid. Sole-sourcing the equipment trades a small cost premium for schedule certainty and platform continuity, judged worth it given the lead-time risk on the Risk Register. |
| Prepared By / Date | R. Owens, Veritas Concept Engineering / September 2026 |

7. FRS Scoring Summary — filled example

An honest 87 out of 100, not a rounded-up 100. The two categories that lose the most points — Site & Physical/Regulatory Constraints and Risk & Approval Readiness — are exactly the ones with open items on the Risk Register and Approval & Timeline Map above; the score reflects the real state of the package, not just its overall soundness.

| FRS Category | Weight | Score Achieved | Established By |
| --- | --- | --- | --- |
| Business Case & Funding Clarity | 12 | 12 | Phase 1 — Gate 1 Decision Record |
| Stakeholder Governance & Decision Rights | 8 | 7 | Phase 1 |
| Capacity, Layout & Flow Validation | 22 | 20 | Phase 2 — Capacity & Machine Count, Space & Density, Flow & Travel-Distance Tracker |
| Site & Physical/Regulatory Constraints | 10 | 8 | Phase 2 — Site & Circulation Flow Worksheet |
| Budget Basis & Cost Realism | 15 | 13 | Phase 3 — Cost Estimate Summary |
| Schedule Realism & Sequencing | 10 | 8 | Phase 3 — Schedule Summary & Long-Lead Items Worksheet |
| Risk & Approval Readiness | 9 | 7 | Phase 3 — Risk Register & Approval and Timeline Map |
| Delivery & Procurement Strategy | 14 | 12 | Phase 3 — Delivery & Procurement Strategy Worksheet |
| TOTAL | 100 | 87 | — |

8. Gate 3 Decision Record — filled example

The formal decision, with both the CFO/Finance Lead's and the Facilities Director's sign-off — and a rationale that names the two open risks directly instead of writing around them. This is what Phase 4 starts from.

| Project / Initiative Name | SMT Assembly & Test Line Expansion — Building 2 |
| --- | --- |
| FRS Total Score (out of 100) | 87 |
| Threshold Band Reached — mark one: ☐ 80-100 Candidate for Gate 3 Review ☐ 60-79 Additional Definition Required ☐ Below 60 Not Ready for Gate 3 | 80-100 Candidate for Gate 3 Review (this box checked) |
| Cost Estimate Basis & Amount | $965,000 total installed cost — GC budgetary proposal plus firm vendor equipment quotes; contingency sized at 6.2% given the locked Phase 2 scope |
| Schedule Summary — Key Milestone Dates | Design Development Oct-Dec 2026; permitting and long-lead procurement concurrent; construction Feb-May 2027; commissioning May-Jun 2027; full Year 1 throughput ramp complete by Aug 2027 |
| Top Risks Called Out | Pick-and-place equipment lead time (22 weeks, schedule-critical); utility company 208V service upgrade scheduling; construction tie-in disruption to existing Lines 1-2 production |
| Decision — mark one: ☐ Approved, proceed to Phase 4 ☐ More information needed ☐ Project stopped | Approved, proceed to Phase 4 (this box checked) |
| Rationale | An FRS score of 87/100 (Candidate for Gate 3 Review) reflects a well-defined scope carried forward intact from Gate 2, a cost estimate grounded in firm vendor quotes for the largest line item, and risks with named owners and stated mitigations. The two open items — utility scheduling and the pick-and-place lead time — are being actively managed, not ignored, and don't change the fundamental soundness of the numbers. |
| Phase 4 Budget / Resources Authorized (if approved) | $965,000 capital authorization, plus a $45,000 owner's contingency reserve held outside the project budget for the CFO's discretion |
| Approved By — CFO / Finance Lead — Name, Title, Signature, Date | [Name], Chief Financial Officer, [signature], [date] |
| Approved By — Facilities Director — Name, Title, Signature, Date | [Name], Facilities Director, [signature], [date] |