VERITAS CONCEPT ENGINEERING

Facilities Planning Consulting — Robin Owens

# FRF Phase 4 — Worked Example

Illustrative sample data for all seven Phase 4 templates

This shows Phase 4 filled in, not blank — the closing chapter of the same fictional company used in the Phase 1, Phase 2 Step 1, and Phase 3 Worked Examples. It picks up immediately after the (fictional) Gate 3 Decision Record: scope locked, a $965,000 cost estimate built from real quotes, and an honest 87/100 FRS score. Sample answers are shown in navy to distinguish them from the actual blank Facilitator Guide.

Notice how Phase 4 doesn't re-litigate anything — it compiles. The Funding Package Summary pulls one line from each of the Gate 1, Gate 2, and Gate 3 Decision Records rather than restating the underlying analysis, and every other template either cites a specific Phase 2/3 document or adds something genuinely new to this phase: a formal dollar ask with a named approval authority, a log of real conditions raised and closed before the vote, a locked baseline with an explicit Change Control Threshold, and a governance charter that names an actual person as Project Manager instead of leaving execution ownership implicit.

The numbers stay consistent with the Phase 3 example rather than getting rounded off: the $965,000 project budget and $45,000 contingency reserve are exactly what the fictional Gate 3 Decision Record authorized, and the 87/100 FRS score carries forward unchanged — Phase 4 doesn't re-score the project, it acts on the score Phase 3 already produced.

1. Funding Package Summary — filled example

One document a board or ELT member could read cover-to-cover — every field here traces back to a specific Gate 1, 2, or 3 Decision Record, not restated from memory.

| Project / Initiative Name | SMT Assembly & Test Line Expansion — Building 2 |
| --- | --- |
| Requesting Department / Sponsor | Operations, sponsored by the Chief Operating Officer (Executive Sponsor since Gate 1) |
| Total Capital Requested ($) | $1,010,000 — $965,000 project budget plus a $45,000 contingency reserve held separately by the CFO, per the Gate 3 Decision Record |
| FRS Total Score / Threshold Band (from Phase 3) | 87 / 100 — Gate 3 Approved |
| Business Case Summary (from Phase 1 Gate 1 Decision Record) | SMT Line 2 running at 88% utilization on 2nd shift; two lost/declined RFQs and a top-5 account at risk from lead-time constraints, an estimated $180,000/month in unbilled capacity. Directly supports the 2026-2028 Growth Plan's contract-manufacturer strategy. |
| Selected Scope & Layout Summary (from Phase 2 Gate 2 Decision Record) | Alternative B — SMT Line 3 sited north end of Building 2 in line with Kitting and Reflow/AOI; Functional Test Lab expansion physically separated from the SMT floor for ESD/vibration isolation. 18,500 GSF addition/reconfiguration; 8 net-new machines/stations. |
| Cost & Schedule Basis Summary (from Phase 3 Gate 3 Decision Record) | $965,000 total installed cost, built from firm vendor quotes for the largest line item (equipment) and GC budgetary numbers for construction. 10-month schedule: Design Development Oct-Dec 2026 through Occupancy/Ramp-Up complete Aug 2027. Pick-and-place system's 22-week lead time is the schedule-critical path. |
| Top 3 Risks Carried Forward | 1. Pick-and-place delivery slips past the 22-week quoted lead time (Schedule, High Impact). 2. 208V/3-phase utility service upgrade needs a utility-scheduled outage (Schedule, Medium Impact). 3. Production disruption to existing SMT Lines 1-2 during construction tie-in (Technical/Operational, High Impact). |
| Recommendation | Approve full funding as requested. The scope is locked, the cost estimate is quote-based, and the two highest risks (equipment lead time, tie-in disruption) already have named owners and stated mitigations on the Phase 3 Risk Register — proceeding now protects the 22-week equipment lead time against further slippage. |
| Prepared By / Date | R. Owens, Veritas Concept Engineering / September 2026 |

2. Capital Appropriation Request — filled example

The formal ask, stated as a request — including why this dollar amount needs Executive Leadership Team approval even though it's within the COO's individual authorization ceiling.

| Amount Requested ($) | $1,010,000 total ($965,000 project budget + $45,000 CFO-held contingency reserve) |
| --- | --- |
| Funding Source(s) — operating capital, debt financing, reserve, other | Company's FY2027 Capital Expenditure budget — internally funded from operating capital; no external financing required. |
| Approval Authority Required — who/what body's sign-off this dollar level actually needs | Executive Leadership Team (ELT). Company policy routes any single capital request over $750,000 to ELT for a formal vote, even though the amount is within the COO's individual $1.5M authorization ceiling established at Gate 1. |
| Prior Gate Approvals on File — Gate 1 / Gate 2 / Gate 3 dates | Gate 1 (Need Validated): approved [date]. Gate 2 (Scope Locked): approved August 18, 2026. Gate 3 (Numbers Proven): approved September 2026, FRS 87/100. |
| Contingency Requested Separately? (Y/N, amount, and who controls release of it) | Yes — $45,000, held by the CFO outside the $965,000 project budget line item. Released only against a documented cost overrun tied to a specific Risk Register item, not merged into the project budget by default. |
| Requested Decision Date | Early October 2026 ELT meeting — timed to authorize the pick-and-place system's purchase order before the vendor's 90-day quote hold expires and to keep the October 2026 Design Development start on schedule. |
| Prepared By / Date | R. Owens, Veritas Concept Engineering / September 2026 |

3. Board / Committee Presentation Checklist — filled example

A completeness check, not a content summary — confirms every piece of the Phase 1-3 package is actually attached and assigns who presents each piece.

| Item | Attached? | Presenter | Notes |
| --- | --- | --- | --- |
| Funding Package Summary | Yes | R. Owens | Covers scope, layout, and recommendation |
| Capital Appropriation Request | Yes | CFO / Finance Lead | States the exact ask and required authority |
| Gate 1 Decision Record | Yes | COO (Executive Sponsor) | Business case origin |
| Gate 2 Decision Record | Yes | R. Owens | Locked scope and layout |
| Gate 3 Decision Record & FRS Scoring Summary | Yes | CFO / Finance Lead | 87/100, Gate 3 Approved |
| Cost Estimate Summary (Phase 3) | Yes | CFO / Finance Lead | $965,000, category-by-category |
| Schedule Summary & Long-Lead Items Worksheet (Phase 3) | Yes | Facilities Director | Pick-and-place lead time flagged |
| Risk Register & Key Assumptions (Phase 3) | Yes | Facilities Director | 6 risks, all with named owners |
| Delivery & Procurement Strategy Worksheet (Phase 3) | Yes | Facilities Director | Design-Bid-Build + sole-source equipment |

4. Conditions & Follow-Up Items Log — filled example

Three real conditions raised during the presentation, each closed out with a named owner before the vote — plus one genuinely still-open item (FF&E vendor selection) that's tracked here but correctly NOT listed as a condition of approval on the Gate 4 Decision Record below.

| Item Raised | Raised By | Response / Resolution | Owner | Status | Due Date |
| --- | --- | --- | --- | --- | --- |
| Confirm the utility company's 208V service-upgrade timeline before committing to the Oct 2026 Design Development start | CFO | Utility coordination meeting held Sept 22 — initial application confirmed accepted, 16-20 week estimate holds | Facilities Director | Closed | Sep 25 2026 |
| Verify the pick-and-place vendor's quote is still valid given the time elapsed since the Cost Estimate Summary was prepared | CFO | Vendor reconfirmed pricing valid through December 2026, beyond the requested PO date | R. Owens | Closed | Sep 26 2026 |
| Name the Project Manager / Owner's Representative before funds are released, not after | COO (ELT) | Facilities Director confirmed as Project Manager / Owner's Representative, effective on Gate 4 approval | Facilities Director | Closed | Oct 1 2026 |
| Confirm FF&E vendor selection is finalized before the Construction/Installation milestone | CFO | In progress — RFQ out to 3 vendors, decision due mid-November 2026 | R. Owens | Open | Nov 15 2026 |

5. Project Baseline Record — Scope, Cost & Schedule — filled example

The specific authorized numbers, cited back to the exact Phase 2/3 documents — plus a Change Control Threshold stated in real dollar and schedule terms, not left as a vague "significant change" standard.

| Approved Total Project Cost ($) | $965,000 |
| --- | --- |
| Approved Contingency ($ and %) | $45,000 (4.7% of total), held separately by the CFO — not part of the $965,000 baseline |
| Approved Completion Date | August 2027 (Occupancy/Ramp-Up complete) |
| Baseline Scope Reference — cite the exact Phase 2/3 documents this baseline is drawn from | Phase 2 Gate 2 Decision Record (Alternative B layout, 18,500 GSF, dated August 18, 2026); Phase 3 Cost Estimate Summary and Schedule Summary & Long-Lead Items Worksheet (both dated September 2026) |
| Baseline Established Date | October 2026 (Gate 4 approval date) |
| Change Control Threshold — dollar amount and/or schedule slip that triggers mandatory re-approval, not a routine field decision | Any single change order exceeding $25,000, any cumulative change exceeding $75,000, or any schedule slip exceeding 3 weeks on a schedule-critical milestone (Design Development, Long-Lead Procurement, Construction/Installation) requires ELT re-approval before proceeding. |
| Prepared By / Date | R. Owens, Veritas Concept Engineering / October 2026 |

6. Execution Governance & Change Control Charter — filled example

A named Project Manager and a three-tier decision authority matrix — the Facilities Director can act alone on small changes, but the Change Control Threshold routes anything larger back to the body that actually approved the funding.

| Project Manager / Owner's Representative Assigned — Name, Title | [Name], Facilities Director |
| --- | --- |
| Decision Authority Matrix — who can approve what dollar level of change without going back to the Gate 4 approving body | Facilities Director (Project Manager): up to $10,000 without escalation. CFO / Finance Lead: $10,001-$25,000. Executive Leadership Team: required at or above the $25,000 single-change / $75,000 cumulative Change Control Threshold, or any schedule-critical slip beyond 3 weeks. |
| Change Order Approval Process — steps, required documentation, sign-offs | Facilities Director logs every proposed change on a Change Order Request tied to a specific Risk Register or Assumption item; CFO/Finance Lead reviews cost impact; sign-off required at the appropriate authority level above before work proceeds; every approved change updates the Project Baseline Record. |
| Reporting Cadence to Leadership — frequency, format, what triggers an out-of-cycle report | Monthly written status report to the CFO and COO — cost-to-date vs. baseline, schedule status vs. milestone dates, open Risk Register items. Immediate out-of-cycle report the same week the Change Control Threshold is approached, not just when it's crossed. |
| Escalation Path — who gets notified, in what order, if the Change Control Threshold is hit | Facilities Director → CFO/Finance Lead → COO (Executive Sponsor) → Executive Leadership Team, triggered automatically. |
| Prepared By / Date | R. Owens, Veritas Concept Engineering / October 2026 |

7. Gate 4 Decision Record — filled example

The formal close of FRF for this project. Three separate approval lines, and a rationale that credits the resolved conditions and the still-open risks by name rather than a generic "looks good."

| Project / Initiative Name | SMT Assembly & Test Line Expansion — Building 2 |
| --- | --- |
| Total Capital Authorized ($) | $1,010,000 — $965,000 project budget + $45,000 CFO-held contingency reserve |
| Facility Readiness Score — Carried from Gate 3 (out of 100) | 87 |
| Reconfirmed at Gate 4 — No Material Change to Scope, Cost, Schedule, Risk, or Operational Assumptions Since Gate 3? | Yes, reconfirmed as-is (this box checked) — no material change since the September 2026 Gate 3 decision. |
| If Not Reconfirmed — What Changed, and Which Phase Was Reopened | N/A — reconfirmed as-is. |
| Conditions Attached to This Approval (if any) | None outstanding at the time of the vote — the three conditions raised during presentation (utility timeline, vendor quote validity, Project Manager assignment) were resolved and closed beforehand. The open FF&E vendor selection is tracked as a normal execution item on the Conditions & Follow-Up Items Log, not a condition of this approval. |
| Decision — mark one: ☐ Approved, proceed to execution ☐ Approved with conditions ☐ Deferred — more information needed ☐ Declined | Approved, proceed to execution (this box checked) |
| Rationale | An 87/100 FRS score, a cost estimate grounded in firm vendor quotes, a named Project Manager, and a locked baseline with an explicit Change Control Threshold gave the ELT confidence to approve without further delay. The two risks still open on the Phase 3 Risk Register — utility scheduling and tie-in production disruption — are being actively managed under the Execution Governance & Change Control Charter, not a reason to withhold funding. |
| Project Manager / Owner's Representative Assigned | [Name], Facilities Director |
| Baseline Established Date (from Project Baseline Record) | October 2026 |
| Approved By — Board Chair / Executive Sponsor — Name, Title, Signature, Date | [Name], Chief Operating Officer (Executive Sponsor), [signature], [date] |
| Approved By — CFO / Finance Lead — Name, Title, Signature, Date | [Name], Chief Financial Officer, [signature], [date] |
| Approved By — Facilities Director — Name, Title, Signature, Date | [Name], Facilities Director, [signature], [date] |